# Sprint: Direct CUDA Embedding (27h → 36min)

**Priority:** P0 — Blocks 700GB indexing on work desktop

**Estimated Impact:** 45x embedding speedup

**Sprint Owner:** TBD (assign team)

**Repo:** HybridRAG3_Educational

**Date:** 2026-03-25

## Background

Embedding 700GB (460K files, 11.5M chunks) currently takes ~27 hours due to sequential HTTP round-trips to Ollama. Direct CUDA embedding via sentence-transformers eliminates the HTTP overhead entirely.

All 3 machines have 12GB+ GPU (Beast: dual 3090 48GB, work desktop: Blackwell, work laptop: Blackwell). No CPU fallback needed.

## Slice 1: Requirements + Approvals (1 hour)

**Owner:** Documentation lead

**Files:** `requirements_approved.txt`

- [ ] Add `torch==2.6.0` (BSD-3, Meta/USA — note: Meta BANNED for models, torch library itself is fine)

- [ ] Add `sentence-transformers==4.1.0` (Apache 2.0, UKP Lab/Germany)

- [ ] Add transitive deps: `transformers`, `tokenizers`, `safetensors`, `huggingface-hub`

- [ ] Mark all as APPLYING with license + origin

- [ ] Document: "Added for 45x embedding speedup. Ollama retained for LLM inference only."

- [ ] Verify no China-origin packages in the dependency chain

**Acceptance:** `pip install -r requirements_approved.txt` succeeds cleanly

## Slice 2: Embedder Rewrite (2-3 hours)

**Owner:** Core coder

**Files:** `src/core/embedder.py`

- [ ] Add `SentenceTransformer` import with try/except fallback

- [ ] New method `_embed_direct_cuda(texts)` using `model.encode(texts, batch_size=256, device='cuda')`

- [ ] Modify `embed_batch()`: try direct CUDA first, fall back to Ollama HTTP if torch unavailable

- [ ] Auto-detect GPU at init: `torch.cuda.is_available()`

- [ ] Log which path is active: "Embedding via direct CUDA (45x)" or "Embedding via Ollama HTTP (fallback)"

- [ ] Set `OLLAMA_NUM_PARALLEL=1` for Ollama path (bug #6262)

- [ ] Respect `HYBRIDRAG_EMBED_BATCH` env var (default 256 for CUDA, 64 for Ollama)

- [ ] Keep model name configurable: `nomic-embed-text` default, `nomic-embed-text-v2-moe` option

- [ ] Handle OOM gracefully: if CUDA OOM, halve batch size and retry

**Acceptance:**

```python

from src.core.embedder import Embedder

e = Embedder()

# Should print "Embedding via direct CUDA"

vecs = e.embed_batch(["test"] * 256)

assert vecs.shape == (256, 768)

```

## Slice 3: Config Update (30 min)

**Owner:** Core coder

**Files:** `config/config.yaml`, `src/core/config.py`

- [ ] Add `embedding.device: auto` (auto/cuda/cpu)

- [ ] Add `embedding.batch_size: 256`

- [ ] Add `embedding.model_path: nomic-ai/nomic-embed-text-v1.5` (HuggingFace model ID)

- [ ] Remove `device: str = "cuda"  # Unused` comment from config.py

- [ ] Wire new config fields into Embedder constructor

**Acceptance:** `jcoder doctor check` shows embedding device correctly

## Slice 4: Documentation Updates (2 hours)

**Owner:** Documentation lead

**Files:** 6 docs

- [ ] `docs/01_setup/INSTALL_AND_SETUP.md` — Add "GPU Embedding Setup" section

- torch install command: `pip install torch --index-url https://download.pytorch.org/whl/cu121`

- sentence-transformers install

- First-run model download note (nomic-embed-text auto-downloads ~500MB)

- Verify: `python -c "import torch; print(torch.cuda.is_available())"`

- [ ] `docs/01_setup/MANUAL_INSTALL.md` — Same GPU section

- [ ] `docs/02_architecture/TECHNICAL_THEORY_OF_OPERATION_RevC.md`

- Update embedding pipeline diagram: "Ollama HTTP" → "Direct CUDA (sentence-transformers)"

- Add note: "Ollama retained for LLM inference. Embeddings use direct GPU for 45x speedup."

- [ ] `docs/05_security/waiver_reference_sheet.md` — Add torch + sentence-transformers entries

- [ ] `docs/03_guides/AUTOTUNE_CHEAT_SHEET.md` — Update if embedding timing is referenced

- [ ] `CLAUDE.md` — Add: "Embedding uses direct CUDA. Ollama is for LLM only."

**Acceptance:** Fresh reader can follow install guide and get CUDA embedding working

## Slice 5: Indexer Integration (1 hour)

**Owner:** Core coder

**Files:** `src/core/indexer.py`

- [ ] Add `multiprocessing.Pool(workers=8)` for file parsing (8x speedup on parsing stage)

- [ ] Add batch SQLite commits (1000 chunks per commit instead of 1)

- [ ] Log embedding throughput: "Embedding: X chunks/sec (direct CUDA)" during indexing

- [ ] Add progress bar with ETA based on throughput

**Acceptance:** Index 1000 files and verify:

- Embedding uses CUDA (check log)

- Parsing uses multiple cores (check CPU usage)

- SQLite commits are batched (check I/O pattern)

## Slice 6: Testing (1 hour)

**Owner:** QA

**Files:** `tests/`

- [ ] `test_embedder_cuda.py` — Test direct CUDA embedding produces correct dimensions

- [ ] `test_embedder_fallback.py` — Test Ollama fallback when torch unavailable

- [ ] `test_embedder_batch.py` — Test batch sizes 64, 128, 256, 512

- [ ] `test_embedder_oom.py` — Test OOM recovery (halve batch + retry)

- [ ] Run full regression: all 1,296 tests still pass

- [ ] Benchmark: time 10,000 chunk embedding via CUDA vs Ollama HTTP

**Acceptance:** All new + existing tests pass. Benchmark shows >10x speedup.

## Slice 7: Env Var Setup Script (30 min)

**Owner:** DevOps

**Files:** `tools/setup_gpu_embedding.bat` (new)

- [ ] Create one-click setup script:

```batch

@echo off

echo Setting up GPU embedding environment...

setx OLLAMA_FLASH_ATTENTION 1

setx OLLAMA_KEEP_ALIVE 24h

setx OLLAMA_MAX_LOADED_MODELS 2

setx OLLAMA_NUM_PARALLEL 1

setx HYBRIDRAG_EMBED_BATCH 256

echo Done. Restart Ollama for changes to take effect.

```

- [ ] Add to INSTALL_AND_SETUP.md as post-install step

**Acceptance:** Running script + restarting Ollama = all env vars set correctly

## Timeline

| Slice | Est. Hours | Dependency |

|-------|-----------|------------|

| 1. Requirements | 1h | None |

| 2. Embedder rewrite | 2-3h | Slice 1 |

| 3. Config update | 0.5h | Slice 2 |

| 4. Documentation | 2h | Slice 2 |

| 5. Indexer integration | 1h | Slice 2 |

| 6. Testing | 1h | Slices 2-5 |

| 7. Env var script | 0.5h | None |

| **TOTAL** | **8-9 hours** | |

**Can parallelize:** Slices 1+7 (no deps), then 2+3+4 (parallel after 1), then 5+6.

**Critical path:** Slice 1 → Slice 2 → Slice 6 = ~5 hours minimum.

## Success Metrics

| Metric | Before | After | Target |

|--------|--------|-------|--------|

| 700GB embed time | 27 hours | <1 hour | 45x speedup |

| Parsing time | 6.4 hours | <1 hour | 8x speedup |

| Total index time | 35 hours | <3 hours | 12x speedup |

| Tests passing | 1,296 | 1,296+ | No regression |

Signed: Claude Opus 4.6 | Sprint Plan | 2026-03-25 19:50 MDT